## excel(1)
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 25.7 | 15.5 | 18.1
Planned Time | 0.27708 |  | 0.90208
Actual Tiempo |  | 0.34514 | 0.93194
CPI (Cost-Performance Index) |  |  | 0.97
% Reuse | 13.2% | 16.9% | 7.43%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 14.5 | 7.81 | 12.4
Total Defects/KLOC or equivalent | 36.2 | 31.2 | 34.7
Yield % | 50% | 75% | 57.1%
Code Review Rate | #DIV/0! | 512 | 1616
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:57 AM el 6/03/2017